## bug report
PRODUCT
| LABELS | HOSPITAL(WEBSITE)
| TESTED BY | KARAN KHERA
| DEVELOPED BY | FRONT END -> MOHIT KUMAR BACKEND-> SUWAMI
| CREATION DATE | 2023-06-28
| REVIEWED BY | ASHIT CHOUDHARY (PROJECT MANAGER)
| TEST ENVIRONMENT /BUILD INFO | TEST ENVIRONMENT -> WINDOWS 11 GOOGLE CHROME MOZILLA FIREFOX MICROSOFT EDGE BUILD INFO-> e6001a5 WEB V 0.1.0
| SCREEN RESOLATION TEST INFO | 1920 x 1080 Screen Width: 1920 pixels Screen Height: 1080 pixels DPR(Device Pixel Ratio): 1 Color depth: 24 bits per pixel Browser viewport(browser window's size without taskbars/toolbars/address bars): Width: 1880 pixels Height: 962 pixels | 1280 x 720 Screen Width: 1280 pixels Screen Height: 720 pixels DPR(Device Pixel Ratio): 1.5 Color depth: 24 bits per pixel Browser viewport(browser window's size without taskbars/toolbars/address bars): Width: 1240 pixels Height: 602 pixels
| PARENT ISSUE TITLE | HOSPITAL ISSUES AFTER NEW CHANGES
| PARENT DEFECT ID | MA-1238
NO | CHILD DEFECT ID | BUG | BUG TYPE | PRIORITY | RESULT
1 | MA -1239 | Create case screen - Old UI can be seen beneath the create case form. Kebab menu, Create case. archived should not be there in the new form for create case. | UI/FUNCTIONALITY | HIGH | FIX
2 | MA - 1241 | Create case screen - scroll bar is working but is not visible properly. | UI | MEDIUM | FIX
3 | MA - 1242 | Create case new form - While filling the form, if user wants to go back after clicking on next, there should be a previous button. | UI/FUNCTIONALITY | MEDIUM | FIX
4 | MA - 1240 | New form - 2nd step - Date of Birth text field should be replaced with age text field. (as per figma) | UI | MEDIUM | FIX
5 | MA - 1243 | New form - 3rd step - while uploading, Clinical history, gross details and radiology image, in figma there is a file shown while uploading. Make it as per figma. | FUNCTIONALITY | HIGH | FIX
6 | MA - 1244 | New form - 3rd step - Clinical history, Gross detail, Radiology image - When user is uploading multiple files, it should not come in the box from where user can drag drop or upload. It should come beside it in another section or this whole can be one section so that user can scroll. | UI/FUNCTIONALITY | HIGH | FIX
7 | MA - 1245 | New form - 3rd step - When image is added, it shows beside the uploading box, there it should not have progress bar when it is just added. The bar will come when the image is uploading. | FUNCTIONALITY | MEDIUM | FIX
8 | MA-1246 | When case is created and user opens the case then hits the back button, he shouldn't be redirected to the new case screen. He should land on the Dashboard. | FUNCTIONALITY | HIGH | FIX
9 | MA-1247 | New form - 2nd step - DOB - When user inputs the date of birth, yyyy doesn't take only four digits, it is taking 6-8 digits. And if user writes 1999 and clicks outside the input box, the value gets automatically changed. | FUNCTIONALITY | MEDIUM | FIX
10 | MA-1279 | Dashboard - When user switch among "new case" and "shared case", the blue line beneath it is not equal. Also Clinical, organ and urgent cases are hidden when shared case is selected. | UI/FUNCTIONALITY | LOW | FIX
11 | MA-1249 | Create new case - 1st step - "Department from" will be before "Departement to" as user enters the current state (in which department he is currently) and in "department to" he will enter the state where he wants to be. | UI | MEDIUM | FIX
12 | MA-1250 | UHID - There should be no space in UHID. when user hit space button because space are not allowed in it | FUNCTIONALITY | MEDIUM | FIX
13 | MA-1251 | Create case new form - 1st step - When one case is created with one ID, and user creates another case, the case ID text field is not updated. User is able to create case with the same ID. | FUNCTIONALITY | HIGH | FIX
14 | MA-1252 | Create case new form - While creating case, on each step user should have a red boundary with warning if mandatory fields are not filled. User shouldn't be allowed to proceed further without filling the mandatory fields. | UI/FUNCTIONALITY | MEDIUM | FIX
15 | MA-1253 | Create case new form - After creating a case when user clicks on "create another case" user gets redirected to the third part of create case form. He doesn't get a fresh page of create new case. | FUNCTIONALITY | MEDIUM | FIX
16 | MA-1254 | Create case new form - After filling all the information in the form, when user hits the cancel button or he clicks on the logo or the cases option in the header, after getting redirected to the dashboard when he again opens the create case form all the fields are filled with the previous information. He doesn't gets the refereshed page. | FUNCTIONALITY | MEDIUM | FIX
17 | MA-1255 | When case is created successfully, there is a field name as "Assign to" here case is to clinician or doctor (pathologist) is not clear. "Assign to" gives an understanding that case is assigned to a doctor which is not done while creating a case. | FUNCTIONALITY | MEDIUM | FIX
18 | MA-1256 | Slide is not shown immidiately after uloading in technologist acc. | FUNCTIONALITY | MEDIUM | FIX
19 | MA-1257 | DASHBOARD>CASE>SLIDE->While uploading a slide, user puts the Accession Id name as per choice and selects H&E, slide name it also gets changed. | FUNCTIONALITY | MEDIUM | FIX
20 | MA-1258 | In clinical history, when picture is opened in expanded form, it gets out of the Dialogue box and also if user wants to add description or edits it he is unable to do that. | FUNCTIONALITY | MEDIUM | FIX
21 | MA-1259 | In clinical history, Expanded view picture, In "uploaded by" field, the name written doesn't have any space. | UI | LOW | FIX
22 | MA-1260 | In radiology image, when image is uploaded but name doesn't shows up, whereas in Overview section the name is show for the same. | UI/FUNCTIONALITY | MEDIUM | FIX
23 | MA-1261 | Clinical History Section - Radiology image and clinical history doesn't have the same space. Becasue of that image size gets disturbed. | UI/FUNCTIONALITY | LOW | FIX
24 | MA-1262 | If there is description added in radiology image/gross image, clinical history then user can't edit that. | FUNCTIONALITY | MEDIUM | FIX
25 | MA-1263 | In clinical history, image is getting streched. | FUNCTIONALITY | MEDIUM | FIX
26 | MA-1264 | Radiolody image - If uploading a radiology image while creating new form, then the image is small. But at the same point, when uploading from overview section, the picture gets streched. | FUNCTIONALITY | LOW | FIX
27 | MA-1265 | Create case new form - 3rd step - Instead of Gross detail and radiology detail there should be Gross image and Radiology image. | UI | MEDIUM | FIX
28 | MA-1266 | When any case is open from Dashboard, user does not lands on the overview section, he gets redirected to the previous case selected option. | FUNCTIONALITY | MEDIUM | FIX
29 | MA-1267 | Radiology image, Gross image - When multiple images are there, size of the image is not proper. Description is long, it is not completely shown. Also, only image is shown without description sometimes. | UI/FUNCTIONALITY | MEDIUM | FIX
30 | MA-1268 | When Pathologist reviews the assigned case, then also technologist doesn't gets notified. When the case is being created that time a line comes that "user will get notified if the case is reviewd by the pathologist". As per this line there, this action is wrong. | UI | HIGH | FIX
31 | MA-1269 | after create a case when user open it then user should not see that case is already assigned to self | FUNCTIONALITY | HIGH | FIX
32 | MA-1270 | While uploading any kind of picture through a dialogue box, when images are added, the progress should not be there as at that point not showing any progress. It should come when user hits on save button because then only progress bar comes into picture | FUNCTIONALITY | MEDIUM | FIX
33 | MA-1271 | Overview, slide, report, clinical history, gross image - An unwanted white section is in a downward direction that is useless. Remove that. | UI | MEDIUM | FIX
34 | MA-1272 | TECHNOLOGIST>CASE>CASE TIMELINE-> Case timeline - When a case is created by a technologist and slide is uploaded in that case, it doesn't get reflected in case timeline. It should reflect with how many slides are there, by whom it is created (doctor) with view slide as it is made in Figma. | UI/FUNCTIONALITY | MEDIUM | FIX
35 | MA-1274 | Pathologist>Case>Case timeline-> When a case is assigned to a pathologist by technologist, and pathologist opens the case, in the case timeline notification is missing that case is assigned by whom (technologist name). | UI | MEDIUM | FIX
36 | MA-1273 | Technologist>Case>Case timeline ->When technologist assigns a created case to pathologist, in case timeline doctor word is missing before the name to whom it is assigned. | UI | MEDIUM | FIX
37 | MA-1275 | Pathologist/Technologist>Case>Case timeline-> screen size (1280X720) In case timeline, the information does not get fit in one line, it should come in second line as per figma. It should not be partially shown. | UI | MEDIUM | FIX
38 | MA-1276 | Pathologist>Case>Case timeline-> When pathologist receive a case or he creates a case himself, whe he uploads the slide it doesn't get shown in the case timeline. | FUNCTIONALITY | MEDIUM | FIX
39 | MA-1277 | Case>Case timeline -> When report is submitted, in both case (technologist/pathologist) in case timeline it should come as "report craeted by dr. __." | UI | MEDIUM | FIX
40 | MA-1278 | PATHOLOGIST /TECHNOLOGIST> CASE TIMELINE->hypertext should show on the case timeline, notification and it should redirect user according to their screen that are link with hypertext 1. create case -> view case 2. case assigned -> edit assignment 3. slide upload -> view slide 4. report created -> view report | UI | HIGH | FIX
41 | MA-1280 | Case timeline> Pathologist to Technologist/ Pathologist to pathologist (vice-versa)-> When in a case any report is submitted or any changes are made. It reflects to one account immidiately but other user does not gets notified for it. | FUNCTIONALITY | HIGH | FIX
42 | MA-1281 | Technologist/Pathologist>Case>Overview>Recent slide -> If any is recently uploaded or user has worked multiple times on a particluar slide, only in these two cases slides should be shown under recent slide option. If there is no action on the slide section from two or three days then user should not see it. | FUNCTIONALITY | HIGH | FIX
43 | MA-1282 | Case>Overview>Radiology image -> When image is uploaded, it gets out of the bounding box. in 1920*1080 | UI | HIGH | FIX
44 | MA-1283 | Case craeted> After creating a case, when user gets case created message, in case details an unwanted space is coming where there is no input. | UI | LOW | FIX
45 | MA-1284 | Report -> Gender and age cannot be together in one section. | UI | MEDIUM | FIX
46 | MA-1285 | Report -> In the new form, age has been replaced with DOB. Update that. | UI | HIGH | FIX
47 | MA-1286 | Report -> If user has created case before with age field or user has created case with DOB in new case form, in both the cases when report is viewed there it shows "null". | FUNCTIONALITY | HIGH | FIX
48 | MA-1287 | Report -> In report section, there is no case number written, because of this while viewing it there is shows undefined in front of case number. | UI/FUNCTIONALITY | MEDIUM | FIX
49 | MA-1288 | When pathologist submits the both the report, then also user is obly able to see standard report and is not able to see synoptic report. | UI/FUNCTIONALITY | MEDIUM | FIX
50 | MA-1289 | Report -> If user fills any one report it can be seen with a heading which kind of report it is. | UI | MEDIUM | FIX
51 | MA-1297 | Report -> When in viewer we open the standard report, there is no age shown. | FUNCTIONALITY | LOW | FIX
52 | MA-1290 | Once case is completed, the "case assigned to" field should not be functional. | FUNCTIONALITY | LOW | FIX
53 | MA-1291 | Dashboard-> All the details in the table should be left alignd with the first letter of the heading. | UI | LOW | FIX
54 | MA-1292 | Dashboard -> Case name should be repalced by Case ID. | UI | MEDIUM | FIX
55 | MA-1293 | Report -> While submitting and when on viewer, Case name should be replaced by Case ID. | UI | MEDIUM | FIX
56 | MA-1294 | Dashboard -> New case icon and the words written beside it in the table have no space in between. | UI | LOW | FIX
57 | MA-1295 | Dashboard -> Organ, Clician and all the filters will be in medium and not regular. | UI | LOW | FIX
58 | MA-1296 | On the Dashboard, remove Case dahsbaord text. | UI | LOW | FIX
59 | MA-1248 | DASHBOARD- Clinical, organ and urgent cases are hidden when shared case is selected. | FUNCTIONALITY | MEDIUM | FIX
60 | MA-1298 | NEW CASE-> user should able to logout their profile | FUNCTIONALITY | MEDIUM | FIX